ALL INDIA INSTITUTE OF SPEECH AND HEARING

LIBRARY AND INFORMATION CENTRE

SH/LIC/ARF/2019-20 30.12.19

Submitted to the Director.

Sub: Extension of the ARF project-reg.

Ref: 1.SH/CDN/ARF-Elect-3/2018-19 dtd 09.10.18

2. SH/PL/ARF-Elect-3/2018-19 dtd 15.02.19

Respected Madam,

With reference to the above, an ARF project titled Design and Development of E-learning Platform and Faculty Profile System was started on 1st February 2019.

The following works pertaining to the project have been accomplished as on date:

1. Identification, installation and setting up of the e-learning platform for AIISH.
2. Setting-up of two trial courses, one each in Speech & Hearing and Special education.
3. Pilot trial instruction in one of the courses setup.
4. Incorporation of outcomes and feedback to improvise instruction.
5. Installation and customization of the faculty profile system.

The pending tasks of the project are the following:

1. Setting-up of comprehensive platform for all the academic programmes of the Institute.
2. Hands-on orientation/training for the faculty on e-learning platform and e-content creation.
3. Pre and post-intervention survey of knowledge and attitudes among the faculty making use of e-learning in the process of instruction.
4. Customization of faculty profile system and data entry.

It is kindly requested for an extension of the project period with the tenure of the research officer for another four months from 1st February 2020 to complete the unaccomplished tasks of the project.

Thank you,

Yours faithfully,

Dr. Shijith Kumar C

Principal Investigator of the Project