## Example-1
|  | RISKS & OPPORTUNITIES SHEET | [11 empty] | Doc.No. | MR-F-10
[14 empty] | Rev.No. | 00
[14 empty] | Date: | 15th Feb 2017
Legend * |  | L - Low |  |  | Risk Categorization # |  | Eliminate Risk
|  | M- Medium |  |  |  |  | Reduced Risk | [6 empty] | Updated On
|  | H- High |  |  |  |  | Risk Transfer | [6 empty] | Frequency | 6 Months
Residual Risk
Type of Risk: Business Risk/ Infrastructure Risk/ Operations/ Process/ Administrative
Risk No. | Area | Type of Risk | Process/ Activity | Associated Risk Description/ Opportunities | ISSUES | Likelihood / Consequence (H/M/L)* | Risk Categorization # | Present Control | Actions taken to address column no.E | Responsibility | Target [ Action Plan Implementation ] | Records | Monitoring System | Evaluation of Implementation Status (30.03.2017) | Revised Risk Categorization
External / Internal
1 | AIISH Site | Infrastructure | Boundary Site from Front Gate and Side Gate of the Building | Theft | Internal | H | Residual Risk | Security Staff are deployed at Front Gate and Parking Area where visitors movement is high. | CCTV monitoring. Additional Security measures for checking of people and Vehicle movement | Engineering Section & Security | 30th June 2017 | Minutes of meeting | Monthly | To be Implemented
2 | AIISH Site | Administrative | Vehicle Movements | Accidents/ Incidents | Internal | H | Residual Risk | NIL | Speed boards display. Security Staff to guide/ create awareness for visitors/clients | Security & Transport Mang. | 10th April 2017 | Minutes of meeting | Monthly | To be Implemented
3 | AIISH Buildings | Infrastructure | Buildings | Rainfall | Internal | L | Reduced Risk | Leak proof treatment carried out on building roofs. | NIL | Engineering Section | 11th April 2017 | Minutes of meeting | Quarterly | To be Implemented
4 | AIISH Site | Infrastructure | Boundary, Site, Buildings | Manmade disasters such as Bomb threats, Terrorist attacks, strikes, etc | Internal | H | Residual Risk | NIL | Contingency Plan needs to be established. Emergency Response Team formation and training on handling manmade disasters from external agencies. | Engineering Section & Security | 30th Dec 2017 | Training records | Quarterly | To be Implemented

## Example-2(Electronics)
|  | RISKS & OPPORTUNITIES SHEET | [11 empty] | Doc.No. | MR-F-10
[14 empty] | Rev.No. | 00
[14 empty] | Date: | 15th Feb 2017
Legend * |  | L - Low |  |  | Risk Categorization # |  | Eliminate Risk
|  | M- Medium |  |  |  |  | Reduced Risk | [6 empty] | Updated On
|  | H- High |  |  |  |  | Risk Transfer | [6 empty] | Frequency | 6 Months
Residual Risk
Type of Risk: Business Risk/ Infrastructure Risk/ Operations/ Process/ Administrative
Risk No. | Area | Type of Risk | Process/ Activity | Associated Risk Description/ Opportunities | ISSUES | Likelihood / Consequence (H/M/L)* | Risk Categorization # | Present Control | Actions taken to address column no.E | Responsibility | Target [ Action Plan Implementation ] | Records | Monitoring System | Evaluation of Implementation Status (30.03.2017) | Revised Risk Categorization
External / Internal
1 | Electronics Department | Infrastructure | IT Assets | Loss of Network connectivity | Internal | H | Eliminate Risk | One Leased Line | Installation of backup network (Leased Line) will be ensured with SLA | Electronics Department | 30th June 2017 | Minutes of meeting | Quarterly | To be Implemented
2 | Electronics Department | Operations | Calibration | Delay in providing calibrated measuring equipments | Internal | M | Eliminate Risk | Master Calibration Plan established |  | Electronics Department | 10th April 2017 | Minutes of meeting | Monthly | To be Implemented
3 | Electronics Department | Operations | Calibration | Delay in providing calibrated measuring equipments | Internal | L | Eliminate Risk | Master Calibration Plan established |  | Electronics Department | 10th April 2017 | Minutes of meeting | Monthly | To be Implemented
4 | Electronics Department | Operations | MOPs | Non-adherence of submission of data on MOPs | Internal | L | Eliminate Risk | Submitted during MRM
5 | Electronics Department | Administrative | MOPs | Compliance to organization knowledge | Internal | L | Reduced Risk | Participation in seminars, exhibitions, conferences, etc | Recording of such participation needs to be maintained | Electronics Department | 30th June 2017 | Organization Knowledge records | Quarterly | To be Implemented

## Sheet1
|  | RISKS & OPPORTUNITIES SHEET | [11 empty] | Doc.No. | MR-F-10
[14 empty] | Rev.No. | 00
[14 empty] | Date: | 15th Feb 2017
Legend * |  | L - Low |  |  | Risk Categorization # |  | Eliminate Risk
|  | M- Medium |  |  |  |  | Reduced Risk | [6 empty] | Updated On
|  | H- High |  |  |  |  | Risk Transfer | [6 empty] | Frequency | 6 Months
Residual Risk
Type of Risk: Business Risk/ Infrastructure Risk/ Operations/ Process/ Administrative
Risk No. | Area | Type of Risk | Process/ Activity | Associated Risk Description/ Opportunities | ISSUES | Likelihood / Consequence (H/M/L)* | Risk Categorization # | Present Control | Actions taken to address column no.E | Responsibility | Target [ Action Plan Implementation ] | Records | Monitoring System | Evaluation of Implementation Status (30.03.2017) | Revised Risk Categorization
External / Internal
1 | L&IC | Infrastructure maintenance | Pest control | Damage to resources | Internal | L | Reduced Risk | Application of chemicals | Avoiding planting shrubs/ tress near building and removing branches falling on the walls, timely removal of garbage, ensuring that all the roof drains and downspouts are kept clear of debris, removal of bird nests from the building, sealing all unnecessary holes in the building, and seal around holes for cables and pipes. Keeping the doors and windws in tight fitting and closed. | L&IC and Engineering Section | 30th June 2017 | Registers | Monthly | To be Implemented
2 | L&IC | Infrastructure maintenance | Preservation of books | Unusable books | Internal | M | Reduced Risk | Checking at the time of shelf rectification and sending for binding | Enhanced frequency of checking and repairing of the books with minor damages by the staff, displaying notices/ banners on how to take care of books in the user areas | L&IC | 30th June 2017 | Registers | Monthly | To be Implemented
3 | L&IC | User Service | Book arrangement on shelves | Non-availability of the required books due to misplacement | Internal | M | Reduced Risk | Shelf rectification, classified arrangement of books | Increase the frequency of shelf rectification | L&IC | Implemented | Work instruction | Daily | Implemented
4 | L&IC | Infrastructure | Book lending | Book theft | Internal | H | Reduced Risk | Restricted carrying of personal print books and wearing of aprons, manual vigilence at the entrance | Installed electromagnetic security system | L&IC | Implemented | Records | Daily | Implimented
6 | L&IC | User Service | Online catalogue service | Missing of complete details of resources | Internal | M | Reduced Risk | Use of proprietary software | Use of open source software with varied functionalities | L&IC | 1 Year | Database | Yearly | To be Implemented